## Slide 1: Data Structures and Algorithms -3 (25CS2103E) Project Scheduling System Using DAG and CPM
Team Members
[Name 1]: [Roll No.]
[Name 2]: [Roll No.]
[Name 3]: [Roll No.]
Under the Esteemed Guidance of
[Faculty Name], [Designation], Dept. of [Department]

## Slide 2
Abstract
Introduction
Literature survey
Problem Statement and Objectives
Hardware and Software requirements
Course Outcomes (CO1-CO6) Coverage
Results
Conclusion
Future Scope
Contents

## Slide 3
Abstract
The Project Scheduling System finds an efficient order for completing project tasks.
Tasks are nodes of a Directed Acyclic Graph (DAG); dependencies are directed edges.
Topological Sort gives a valid execution order; a DFS check rejects circular dependencies.
Critical Path Method (CPM) computes the longest dependency path, the critical tasks and the minimum project duration.
Beyond CPM, the system applies string algorithms (KMP, suffix array), advanced DP, max-flow, approximation, randomised and parallel algorithms to plan real project work.
Implemented in Java as a menu-driven console application.

## Slide 4
Introduction
Projects contain many tasks; some cannot start until others finish.
A DAG models this naturally: no task can (directly or indirectly) depend on itself.
CPM answers: what is the shortest possible project time, and which tasks can never be delayed?
Slack = LS - ES. Tasks with slack 0 are critical; others have room to slip.
Real projects also need: finding tasks by name, deciding who does what, planning with limited workers and handling uncertain durations.
These extra needs map to the algorithm families of DSA-3 (CO1-CO6).

## Slide 5
Literature Survey
Kelley & Walker (1959): Critical Path Method; Malcolm et al. (1959): PERT.
Kahn (1962): topological sorting of a DAG in O(V+E).
Knuth, Morris & Pratt (1977): linear-time string matching (KMP).
Ford & Fulkerson (1956); Edmonds & Karp (1972): maximum flow and min-cut duality.
Graham (1966): list scheduling gives a (2 - 1/m) bound for m machines.
Ullman (1975): scheduling with precedence constraints is NP-complete.
Cormen, Leiserson, Rivest & Stein: Introduction to Algorithms (reference text).
Please verify these citations against the originals before submission.

## Slide 6
Problem Statement and Objectives
Problem Statement
Given tasks with durations and dependencies, find a valid order, the minimum completion time and the critical tasks, and support staffing decisions, without hand calculation.
Objectives
Model tasks and dependencies as a DAG and reject cycles (DFS).
Produce an execution order with Topological Sort (Kahn).
Compute ES, EF, LS, LF, slack, critical path and minimum duration (CPM).
Search task names (KMP) and flag near-duplicates (suffix array + LCP).
Plan work with DP, assign workers by max-flow, approximate m-worker schedules.
Estimate risk with Monte Carlo; use parallel prefix sum and work-span analysis.

## Slide 7
Flow Chart
Input
tasks, durations, deps
Build DAG
adjacency list + HashMap
Cycle check
DFS colouring
Topological sort
Kahn + min-heap
CPM
forward + backward pass
Analysis modules on the same DAG (menu options 2-10)
CO2
KMP, suffix array + LCP
CO3
Bitmask DP, subset DP
CO4
Max-flow (Edmonds-Karp)
CO5
Graham approximation
CO6
Monte Carlo, prefix sum
Output: execution order | ES/EF/LS/LF/slack table | critical path | minimum duration | timeline

## Slide 8
CO1 and CO2: Problem Classes, Strategy and String Algorithms
CO1: Evaluate and select a strategy
Substring search: KMP chosen (O(n+m)) over naive rescanning.
NP-hard scheduling: exact bitmask DP if n <= 20, greedy above.
Network flow: task-worker assignment modelled as max-flow.
Menu option 6 prints the problem-class / strategy table.
CO2: String algorithms
KMP: prefix function + linear search over task names.
Suffix array sorts all suffixes of the joined names.
LCP array (Kasai, O(n)) gives shared substring lengths.
Finds B ~ C sharing "database " (9 characters).
Sub-problem | Class | Strategy
Order of tasks | DAG ordering, P | Topological sort O(V+E)
Min project time | Longest path, P | CPM = DP on topological order
One worker | NP-hard | Bitmask DP / greedy
m workers | NP-hard | Graham (2-1/m) approximation

## Slide 9
CO3: Advanced Dynamic Programming
Bitmask DP (DP on subsets)
State: mask = set of tasks already done.
dp[mask] = min sum of finish times; a task is allowed only if its dependency mask is inside mask.
Same table counts valid topological orders (2 for the sample).
Time O(2^n * n), used for n <= 20.
Subset-sum DP: two-team split
can[i][s] = tasks 1..i can make workload s.
Best s near total/2 gives the most balanced split.
Sample: Team 1 = A, D (6 days); Team 2 = B, C, E (7 days).
Time O(n * total/2).
CPM as DP over the DAG
Forward pass: ES(v) = max EF(pred), EF = ES + duration. Backward pass: LF(v) = min LS(succ), LS = LF - duration.
Each value is computed once from already-solved sub-problems, in topological order: O(V+E).
Slack = LS - ES; critical tasks have slack 0, and the longest path is the minimum project duration.

## Slide 10
CO4, CO5 and CO6: Flow, NP-Hardness, Randomised and Parallel
CO4: Network flow
Network: source -> worker (capacity) -> task (skill edge) -> sink.
Edmonds-Karp: BFS shortest augmenting paths, O(V*E^2).
Min-cut is computed from the residual graph; max-flow = min-cut is checked.
Sample: 4 of 5 tasks assigned; total worker capacity is the bottleneck.
CO5: Approximation
Scheduling on m workers contains PARTITION, so it is NP-hard.
Graham list scheduling: start the longest ready task on a free worker.
Guarantee: at most (2 - 1/m) x optimum; checked against lower bound max(critical path, work/m).
Sample, 2 workers: 11 days = lower bound.
CO6: Random + parallel
Las Vegas: randomised quick-select for median duration (always correct).
Monte Carlo: 10000 runs with random delays give expected time, deadline probability, criticality index.
Parallel prefix sum and reduce: span O(log n), verified with Arrays.parallelPrefix.

## Slide 11
Results
Sample project A-E (Requirements, Database Design, Database Setup, Development, Testing)
=== EXECUTION ORDER (Topological Sort) ===
A -> B -> C -> D -> E
=== CPM SCHEDULE ===
ID Task Dur ES EF LS LF Slack Critical
A Requirements 2 0 2 0 2 0 YES *
B Database Design 3 2 5 2 5 0 YES *
C Database Setup 2 2 4 3 5 1 no
D Development 4 5 9 5 9 0 YES *
E Testing 2 9 11 9 11 0 YES *
=== CRITICAL PATH(S) ===
A -> B -> D -> E
Minimum project duration: 11 days
=== TIMELINE (# = critical, - = has slack) ===
A |##
B | ###
C | --
D | ####
E | ##

## Slide 12
Results: Strings, DP and Team Split
[CO2] KMP keyword search for "database":
B Database Design match at index [0]
C Database Setup match at index [0]
[CO2] Suffix array + LCP - similar task names:
B (Database Design) ~ C (Database Setup) shared: "database " (9 chars)
-> Please check that these are not duplicate tasks.
[CO1/CO3] Single worker plan:
Problem: ONE worker does all tasks, respecting dependencies.
Goal : minimise the sum of task completion times (tasks finish as early as possible).
Strategy selected: exact BITMASK DP (n = 5 <= 20, O(2^n * n))
Best order : A -> C -> B -> D -> E
Sum of finish times : 37 (average 7.40 days)
Total time (1 worker) : 13 days
Valid execution orders: 2 (all topological orders, counted by DP on subsets)
[CO3] Two-team split:
Team 1: A D (6 days of work)
Team 2: B C E (7 days of work)
Most balanced split: busiest team has 7 days of work.
(Balances workload only; dependencies may still force waiting between teams.)

## Slide 13
Results: Flow, Approximation, Randomised and Parallel
[CO4] Worker assignment by max-flow:
Network: source -> worker (capacity = max tasks) -> task (1 if skilled) -> sink
Max flow = 4 of 5 tasks assigned
Asha (cap 2): A, B
Ravi (cap 1): D
Meera (cap 1): E
Unassigned tasks: C
Min cut capacity = 4 (max-flow = min-cut: verified)
[CO5] Two workers, approximation:
Problem: schedule tasks on 2 identical workers, minimise finish time (makespan).
Class : NP-hard (2 workers, no dependencies = PARTITION), so exact answers are too costly.
Method : Graham list scheduling (longest ready task first), a polynomial (2 - 1/2)-approximation.
Worker 1: A day 0 -> 2
Worker 1: B day 2 -> 5
Worker 2: C day 2 -> 4
Worker 1: D day 5 -> 9
Worker 1: E day 9 -> 11
Makespan with 2 workers : 11 days
Lower bound on optimum : 11 days = max(critical path 11, ceil(work 13 / 2))
Ratio to lower bound : 1.00 (guarantee <= 1.50)
[CO6] Randomised and parallel:
[Las Vegas] randomised quick-select, expected O(n):
Median task duration = 2 days (always correct)
[Monte Carlo] 10000 runs, each duration grows by 0% to 50% at random (seed 42):
Expected project time = 13.75 days (plain CPM: 11)
P(finish within 13 days) = 19.4%
Criticality index: A 100% B 100% C 0% D 100% E 100%
[Parallel reduce + prefix sum] on task durations in topological order:
Prefix sums (one-worker finish times): [2, 5, 7, 11, 13] [matches Arrays.parallelPrefix]
Total work = 13 days | reduce: 4 additions, span 3 rounds
Work-span: work = O(n), span = O(log n), parallelism ~ n/log n = 1.7

## Slide 14
Hardware and Software requirements
Hardware
Any laptop or PC
Dual-core CPU, 4 GB RAM
Minimal disk space (< 10 MB)
No GPU or network needed
Software
Java JDK 11 or newer (tested on JDK 21)
Windows / Linux / macOS
VS Code, IntelliJ or Eclipse (or terminal)
Run: javac ProjectScheduler.java, then java ProjectScheduler
PowerPoint for the report

## Slide 15
Conclusion
The system builds a DAG, rejects cycles, orders tasks and finds the critical path and minimum duration (11 days on the sample).
Course topics were used where they solve a real scheduling need, not added for their own sake.
Each algorithm was chosen after classifying the sub-problem: polynomial (topological sort, CPM, max-flow), NP-hard (bitmask DP for small n, approximation for m workers), probabilistic (Monte Carlo).
Results were checked: max-flow = min-cut, prefix sums match Java's parallelPrefix, small cases verified by hand.

## Slide 16
Future Scope
Graphical interface with a network diagram of the DAG.
Read projects from CSV or Excel files.
Resource levelling and cost-based crashing of critical tasks.
PERT with three-point estimates (optimistic, likely, pessimistic).
Truly parallel forward pass using Java threads or ForkJoin.
Rabin-Karp and suffix automaton for large task databases.

## Slide 17
Thank you